## Cover
TEST PLAN
Project Name | Quizlet Website |  |  | Reviewer | Le Phi Hung
Project Code | DA |  |  | Review date
Creator | Huynh Ai Quoc / Tran Nhat Thy |  |  | Approver
Version | v1.0 |  |  | Approval Date
Record of change
Effective Date | Version | Change Item | A, D, M | Change description
2022-01-11 | v1.0 | Initial | A
Index
Sheet Name | Description |  |  |  | Note
Cover | Title page
Test Policy | - General policy for Test process, Test case design, Test Data - List of requirements to Test/not Test - Exit criteria for testing - Suspension criteria and Resumption requirements
Test Management | - Test scope - Deliverable - Management method - Risk - Assumption - Training plan
Test Strategy | Identification of Test level, Test types, Test environments, Test data and Enviroment for test
Master Schedule | Introduction and Define team, master schedule for testing
Appendix | - Description and detailed definition of Test level, types and techniques - List of Terminologies and definition/explanation |  |  |  | For Reference only
Reference Document
Name |  |  |  | Version | Note
Note on E10: - A: Added - D: Deleted - M: Modified

## Test Policy
Test Policy
Test process policy
Description of policies of testing process.
| # | Description | Responsibility | Note
1
2
Test case design policy
Description of policies of test case design.
| # | Items | Note
1
2
Quality metric
Description of target
| # | Items | Target | Note
1
2
Pass/Fail Criteria
The conditions that the testing must satisfy to end test.
| # | Criteria | Priority | Note
| 1 | 80% of completed test cases / total test cases (test coverage > 80%) |  | Carry out test cases with highest priority first, then increase gradually.
| 2 | Test successful coverage >= 80%
| 3 | Software is correct with SRS
| 4 | The system runs smoothly on different web browsers (Firefox and Google Chrome latest version).
| 5 | High system security
Suspension Criteria and Resumption Requirements
Specify when to pause in a series of tests and requirements for resumption of test activities.
| # | Suspension Criteria | Note
| 1 | When a defect is introduced that cannot allow any further testing
| 2 | A specific holiday shuts down both development and testing (Tet Holiday)
| 3 | If there is any network, hardware problem in the organisation, we can suspend testing
| 4 | If we got more pending requests with the development team
| # | Resumption Requirements | Note
| 1 | When the particular issue has been addressed and solved

## Test Management
Test Management
Test Scope
Listing of test items in test process.
# | Items | Description |  | Responsibility | Note
1 | Create test plan | Huynh Ai Quoc |  | Tester
2 | Create test design | Huynh Ai Quoc |  | Tester
3 | Create test cases | Huynh Ai Quoc |  | Tester
4 | Create test data |  |  | Tester
5 | Execute function test | Huynh Ai Quoc |  | Tester
6 | Defects list |  |  | Tester
7 | Create test report | Tran Nhat Thy |  | Leader
Deliverables
Listing of documents will be delivered of test process.
# | Deliverables | Delivered date | Delivered by | Delivered to | Note
1 | Test plan | 2022-08-05 | Test leader | Test manager, Team | This document itself
2 | Test cases | 2022-06-29 | Test leader | Test manager, Team
3 | Defect logs |  | Test leader | Test manager, Team
4 | Test report |  | Test leader | Test manager, Team
Management method
Describe the management method of test process.
# | Object | Method |  |  | Note
1
2
3
Risks
Listing of all risks of test process and action to mitigate the risk and do if risk become reality.
# | Condition |  | Mitigation |  | Contingency
1 | Team members lack experience in software testing domain |  | Plan training course to skill up your members |  | 1. Connect with a training organization 2. Attend mandatory training 3. Quality test 4. Organize seminars on software issues
2 | The development team improved the code which led to the testing process being paused |  | Accept this risk |  | 1. Contact the development team 2. Connect the development team and test team
3 | The project schedule is too tight; it's hard to complete this project on time |  | Set test priority for each test case and execute the test case with the highest priority |  | 1. Determine the priority for each test case 2. Set priority for each test case 3. Follow the priority level
4 | Members misunderstood the request |  | Organize to review and analyze requirements to member before starting the testing process |  | 1. Hold a meeting 2. Review required 3. Inspections
5 | Employees reduce working performance after Tet holiday |  | Accept this risk |  | OT to keep up with the schedule
6 | The cost of testing exceeded the budget |  | Accept this risk |  | Contact the project manager
Assumption
Listing of all assumption of test process.
# | Type | Description
1
2
Training Plan
Plan training for test team.
# | Training Topic | Description |  | Responsibility | Start Date | End Date
1
2
3
Note on E32: steps keep a risk from occurring or driving its impact to an acceptance level
Note on G32: steps would have to be done if the risk were to become reality
Note on B42: It can be: - Requirement - Test Products - Test environment - Test tools ...

## Test Strategy
Test Strategy
Test Objective:
To ensure doesn’t contain serious bugs before release to customer, to confirm that the system has met the requirements
Test stages & techniques
Listing of all test stages of project, and test techniques must be done of every test stages.
Test stage | Unit testing | Integration Testing | System Testing | User acceptance testing
Test techniques
White box testing | x |  | x
Black box testing |  | x | x | x
Responsibility | Developer | Tester | Tester | Tester
Requirements to be tested
Listing of what is to be tested from the USERS viewpoint of what the system does.
Feature/Function |  | Document which is testing base on |  |  | Note
All Functions of the DA system described in screen design document, the functions are tested in order of priority from high to low (highest priority tested first) |  | DA_ScreenDesign_V0.5
Test environment
Listing of environments use in test process.
Type | Environment |  |  |  | Note
Hardware | Laptop, Tablet, Smartphone |  |  |  | Standard Fsoft
OS | Window 10 64bit Mac10.14.5 Android 6.0 or higher
Software | Chrome version 78.0.3904.97 Firefox 70.0 Edge 44.18362.329.0
Database | MS SQL
Browser | IE/FireFox, Chrome
Network configured | LAN Wifi
Note on G10: - manual - test tool …

## Master Schedule
Master Schedule
Project Team
Listing of all workers join the testing process
# | Worker / Doer | Position | Responsibilities
1 | 18130096_HuynhAiQuoc | Member | - Create Q/A. - Create Test Plan - Create Test Case: chức năng tạo học phần, học, thẻ ghi nhớ, viết, đăng nhập, đăng ký, đăng xuất - Execute test and logs bugs: chức năng tạo học phần, học, thẻ ghi nhớ, viết, đăng nhập, đăng ký, đăng xuất
2
3
4
5 |  |  | .
Master Schedule
# | Item | Start Date | End Date
1 | Create test plan | 2022-04-05 | 2022-04-12
2 | Create test design | 2022-04-12 | 2022-04-18
3 | Create test case | 2022-04-18 | 2022-04-25
4 | Execute test and log bugs | 2022-04-25 | 2022-05-15
5 | Evaluting exit criteria & Test report | 2022-05-15 | 2022-05-29
6 | Review | 2022-05-29 | 2022-06-29
| Task | Start day from 9/12/2019 | Duration
| Create test plan | 0 | 7
| Create test design | 6 | 6
| Create test case | 11 | 7
| Execute test and log bugs | 17 | 20
| Evaluting exit criteria & Test report | 36 | 14
| Review | 49 | 32
Detail Schedule
Liên kết

## Detail Schedule
# | Item | Responsibilities | April |  |  |  | May | [41 empty] | June
|  |  | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
1 | Create test plan | Team | bar: April 28; May 2; May 7
2 | Create test design | bar: May 12; May 14; May 16; May 18
2019-01-02 | Học | Huỳnh Ái Quốc | bar: May 12 to May 16
2019-02-02 | Tạo học phần | Huỳnh Ái Quốc | bar: May 12 to May 16
2019-03-02 | Viết | Huỳnh Ái Quốc | bar: May 12 to May 16
2019-04-02 | Thẻ ghi nhớ | Huỳnh Ái Quốc | bar: May 12 to May 16
2019-05-02 | Đăng nhập, đăng ký, đăng xuất | Huỳnh Ái Quốc | bar: May 12 to May 16
2019-06-02 | Review | Team | bar: May 17 to May 18
3 | Create test case | bar: May 19
2019-01-03 | Học | Huỳnh Ái Quốc | bar: May 19 to May 24
2019-02-03 | Tạo học phần | Huỳnh Ái Quốc | bar: May 19 to May 24
2019-03-03 | Viết | Huỳnh Ái Quốc | bar: May 19 to May 24
2019-04-03 | Thẻ ghi nhớ | Huỳnh Ái Quốc | bar: May 19 to May 24
2019-05-03 | Đăng nhập, đăng ký, đăng xuất | Huỳnh Ái Quốc | bar: May 19 to May 24
2019-06-03 | Review | Team | bar: May 25 to May 26
4 | Execute test and logs bug | bar: May 27
2019-01-04 | Học | Huỳnh Ái Quốc | bar: May 27
2019-02-04 | Tạo học phần | Huỳnh Ái Quốc
2019-03-04 | Viết | Huỳnh Ái Quốc
2019-04-04 | Thẻ ghi nhớ | Huỳnh Ái Quốc
2019-05-04 | Review | Huỳnh Ái Quốc
2019-06-04 |  | Team | bar: May 7
5 | Evaluting exit criteria & Test report | Team | bar: May 9
6 | Review | Team | bar: June 22

## Appendix
Appendix
Term definition
# | Term | Definition/explanation
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
17
Glossary
#
1
1
2
3
4
#
4
5
6
7
8
9
10
11
12
13
14